## Sheet1
WNR Project Schedule
Rice University
Week Number |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | Winter Break | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Dates (Friday - Thursday) |  | 9/4/2015 - 9/10/2015 | 9/11/2015 - 9/17/2015 | 9/18/2015 - 9/24/2015 | 9/25/2015 - 10/1/2015 | 10/2/2015 - 10/8/2015 | 10/9/2015 - 10/15/2015 | 10/16/2015 - 10/22/2015 | 10/23/2015 - 10/29/2015 | 10/30/2015 - 11/5/2015 | 11/6/2015 - 11/12/2015 | 11/13/2015 - 11/24/2015 | 11/25/2015 - 12/3/2015 | 12/4/2015 - 12/11/2015 |  | 1/8/2016 - 1/14/2016 | 1/15/2016 - 1/22/2016 | 1/23/2016 - 1/28/2016 | 1/29/2016 - 2/4/2016 | 2/5/2016 - 2/11/2016 | 2/12/2016 - 2/18/2016 | 2/19/2016 - 2/25/2016 | 3/4/2016 - 3/10/2016 | 3/11/2016 - 3/17/2016 | 3/18/2016 - 3/24/2016 | 3/25/2016 - 3/31/2016 | 4/1/2016 - 4/7/2016 | 4/8/2016 - 4/14/2016 | 4/15/2016 - 4/22/2016 | 4/23/2016 - 5/2/2016 | Hours By Activity: (Estimated Time) Actual Time
TASK OR DEADLINE: (Estimated Aggregate Time in Hours) Actual Aggregate Time in Hours | [30 empty] | Stephen Xia | Tingkai Liu | Xin Huang | Yuan Gao | TOTAL
PROJECT REQUIREMENTS (% Complete) | LEAD
Meetings
- Check-in meetings with mentors and sponsors | All | (4) 4 | (4) 4 | (4) 4 | (4) 4 | (10) 10 | (4) 4 | (4) 4 | (4) 4 | (4) 4 | (4) 4 | (4) 4 | (4) 4 | (4) 8 |  |  | (4) 4 | (4) 4 | (4) 4 |  | (4) 4 | (4) 4 | (4) 4 | (4) 4 | (4) 4 | (4) 4 | (4) 4 |  | (4) 4 | (4) 4 | (27) 28 | (27) 28 | (26) 27 | (26) 27 | (106) 110
- Undergraduate team meetings | All | (4) 4 | (4) 4 |  |  |  |  | (3) 3 |  | (4) 4 |  | (4) 4 |  | (4) 4 |  | 14: (4) 4; 15: (4) 4 | (8) 8 | (8) 8 | (8) 8 | (7) 7 | (31) 31
Cycle One Documentation (Due 10/23/2015)
- Mission Statement (100%) | Stephen Xia |  |  | (2) 2 | [26 empty] | (2) 2 |  |  |  | (2) 2
- FOSS I Goals (100%) | Xin Huang |  |  | (1) 1 | [28 empty] | (1) 1 |  | (1) 1
- Product Development Worksheet (100%)
- Design Context Review (100%) | Xin Huang |  | (1) 1 | (1) 1 | [28 empty] | (2) 2 |  | (2) 2
- Market Analysis (100%) | Tingkai Liu |  | (1) 1 | (2) 2 | [27 empty] | (3) 3 |  |  | (3) 3
- Customer Needs (100%) | Yuan Gao |  | (1) 1 | (1) 1 | [29 empty] | (2) 2 | (2) 2
- Design Specifications (100%) | Stephen Xia |  | (1) 1 | (1) 1 | [29 empty] | (2) 2 | (2) 2
- Design Foundation Document (100%)
- Design Context Review (100%) | Xin Huang |  | (2) 2 | (12) 16 | [26 empty] | (3) 4 | (2) 2 | (6) 8 | (3) 4 | (14) 18
- Market Analysis (100%) | Tingkai Liu |  | (2) 2 | (6) 8 | [26 empty] | (2) 2 | (6) 8 |  |  | (8) 10
- Customer Needs (100%) | Yuan Gao |  | (2) 2 | (3) 4 | [28 empty] | (2) 2 | (3) 4 | (5) 6
- Design Specifications (100%) | Stephen Xia |  | (2) 2 | (3) 4 | [26 empty] | (3) 4 |  |  | (2) 2 | (5) 6
- Design Strategy (100%) | Stephen Xia | [6 empty] | (16) 16 | [22 empty] | (4) 4 | (4) 4 | (4) 4 | (4) 4 | (16) 16
- Team Contract (100%) | Tingkai Liu | [6 empty] | (10) 10 | [22 empty] | (3) 3 | (3) 3 | (1) 1 | (3) 3 | (10) 10
- Standards and Regulations (100%) | Yuan Gao | [6 empty] | (10) 10 | [22 empty] | (3) 3 | (3) 3 | (1) 1 | (3) 3 | (10) 10
- Product Safety Analysis (FMEA) (100%) | Xin Huang | [6 empty] | (2) 2 | [24 empty] | (2) 2 |  | (2) 2
- Setup SVN; compile documentation online and offline (100%) | Tingkai Liu | [6 empty] | (1) 1 | [23 empty] | (1) 1 |  |  | (1) 1
- List of purchases and expenditures (100%) | Yuan Gao | [6 empty] | (1) 1 | [25 empty] | (1) 1 | (1) 1
Cycle Two Documentation (Due 12/14/2015)
- Cycle Three Functional Specifications (100%) | Stephen Xia | [12 empty] | (1) 1 | [16 empty] | (1) 1 |  |  |  | (1) 1
- Testing Plan and Results (100%) | Yuan Gao | [12 empty] | (1) 1 | [19 empty] | (1) 1 | (1) 1
- IRB Information (100%) | Xin Huang | [12 empty] | (1) 1 | [18 empty] | (1) 1 |  | (1) 1
- Team Safety Plan (100%) | Tingkai Liu | [12 empty] | (1) 1 | [17 empty] | (1) 1 |  |  | (1) 1
- Revisions to Previous Documents (100%) | Xin Huang | [12 empty] | (24) 24 | [16 empty] | (10) 10 | (4) 4 | (6) 6 | (4) 4 | (24) 24
First Prototype (Due 12/11/2015)
- Wireless Transmission (100%)
- Survey wireless/BLE chips (100%) | Xin Huang | (2) 2 | [28 empty] | (1) 1 |  |  | (1) 1 | (2) 2
- Research wireless/BLE technologies (100%) | Xin Huang |  |  |  | (1.5) 1.5 |  | (3) 3 | [25 empty] | (4.5) 4.5 |  | (4.5) 4.5
- Development environment setup (100%) | Yuan Gao |  |  |  | (1) 1 | (3) 3 | [27 empty] | (4) 4 | (4) 4
- CC2650/CC2640 BLE development (100%) | Xin Huang |  |  |  |  | (19) 19 | (6) 9 |  | (6) 6 | (5) 5 | [20 empty] | (23) 25 | (12) 13 | (1) 1 |  | (34) 37
- Nordic Labs BLE development (100%) | Tingkai Liu | [7 empty] | (6) 6 | (21) 21 | (14) 14 | [19 empty] | (16) 16 | (19) 19 | (2) 2 | (4) 4 | (41) 41
- Compression Algorithms (100%) | Yuan Gao |  |  |  |  | (4) 4 | (3) 3 |  |  | (6) 6 | (4) 4 | (2) 2 | (3) 3 | (10) 10 | [19 empty] | (33) 33 | (33) 33
- Research power consumption (100%) | Stephen Xia |  |  |  |  | (3) 3 |  |  |  |  | (2) 2 | [19 empty] | (3) 3 |  |  | (2) 2 | (5) 5
- Research Alternative Wi-Fi Protocol and Components (100%) | Xin Huang | [9 empty] | (1) 1 | (1) 1 | [20 empty] | (2) 2 |  | (2) 2
- TCP/UDP and other error control mechanisms (100%) | Xin Huang | [8 empty] | (3) 3 | (1) 1 | [21 empty] | (4) 4 |  | (4) 4
- TI MSP430F5438 + TI CC2564 Bluetooth Development (100%) | Stephen Xia | [10 empty] | (8) 8 | (11) 11 | (40) 67 | [16 empty] | (56) 83 |  | (3) 3 |  | (59) 86
- Analog Front-End and ADC (100%)
- Survey analog front-end chips for neural recording (100%) | Tingkai Liu | (1) 1 |  |  | (10) 6 |  | (3) 3 |  | (1) 1 | [22 empty] | (15) 11 |  |  | (15) 11
- Research analog front-end circuits for high SNR amplification (100%) | Stephen Xia | (1) 1 |  |  | (4) 4 |  |  |  | (1) 1 | [21 empty] | (4) 4 | (1) 1 | (1) 1 |  | (6) 6
- Research Power Consumption (100%) | Tingkai Liu |  |  |  |  | (2) 2 |  |  |  |  | (4) 4 | [20 empty] | (2) 2 |  |  | (4) 4
- Intan RHD2000 Series Development (100%) | Tingkai Liu | [10 empty] | (8) 8 | (8) 8 | (40) 65 | [17 empty] | (56) 81 |  |  | (56) 81
- Battery Module
- Research technologies (100%) | Xin Huang |  |  |  |  | (2) 2 |  |  | (1) 1 | [23 empty] | (3) 3 |  | (3) 3
- Alternative sources (100%) | Xin Huang |  |  |  |  | (1) 1 |  |  | (1) 1 | [23 empty] | (2) 2 |  | (2) 2
Cycle Three Design Objectives (Due 2/25/2016)
- Wireless Transmission (100%)
- Characterize/Verify BLE throughput on Nordic nRF52 theoretially (100%) | Stephen Xia | [14 empty] | 15: (8) 8 | (5) 5 |  | (3) 3 |  | (8) 8
- Continuously transmit data over BLE from one peripheral to central device (100%) | Stephen Xia | [14 empty] | 16: (7) 7; 17: (21) 21; 18: (12) 12; 19: (40) 40 | (40) 40 | (17) 17 | (23) 23 |  | (80) 80
- Characterize data rate while transmitting continuously over BLE from one peripheral to central device (100%) | Stephen Xia | [14 empty] | 16: (2) 2; 17: (14) 14; 18: (7) 7; 19: (9) 9 | (25) 25 | (7) 7 |  |  | (32) 32
- Continuously transmit data over BLE from at least two peripheral devices to a central device (100%) | Stephen Xia | [14 empty] | 20: (95) 95 | (40) 40 | (40) 40 | (15) 15 |  | (95) 95
- Characterize data rate while transmitting continuously over BLE from at least two peripheral devices to a central device (100%) | Stephen Xia | [14 empty] | 20: (20) 20 | (5) 5 | (5) 5 | (10) 10 |  | (20) 20
- Characterize power consumption of Nordic nRF52 board (100%) | Xin Huang | [14 empty] | 19: (7) 7 |  |  | (7) 7 |  | (7) 7
- Analog Front-End and ADC (100%)
- Run SPI test to read data and measure power consumption (100%) | Tingkai Liu | [14 empty] | 15: (5) 5 |  | (5) 5 |  |  | (5) 5
- Read “fake” data from Intan Chip through SPI and display to confirm the data is actually being received using Nordic nRF52 (100%) | Tingkai Liu | [14 empty] | 16: (9) 9; 18: (5) 5; 19: (10) 10 |  | (24) 24 |  |  | (24) 24
- Characterize/confirm power consumption of the Intan Chip + accessory devices (like LVDS) (100%) | Tingkai Liu | [14 empty] | 18: (5) 5; 19: (9) 9 |  | (14) 14 |  |  | (14) 14
- Compression (100%)
- Implement and characterize compression algorithm (like MiniLZO) (100%) | Yuan Gao | [14 empty] | 15: (7) 7; 16: (6) 6; 17: (10) 10; 18: (6) 6; 19: (5) 5 |  |  |  | (34) 34 | (34) 34
- Implement a compression algorithm (like LZO) on Nordic nRF52 (100%) | Yuan Gao | [14 empty] | 16: (5) 5; 17: (1) 1; 18: (2) 2; 19: (5) 5; 20: (38) 38 | (5) 5 | (5) 5 |  | (41) 41 | (51) 51
- Achieve at least 20% compression on raw data (100%) | Yuan Gao | [14 empty] | 19: (7) 7 |  |  |  | (7) 7 | (7) 7
Cycle Three Logistics and Documentation (Due 2/26/2016)
- Sign up for competitions (100%) | Xin Huang | [14 empty] | 16: (2) 2 |  |  | (2) 2 |  | (2) 2
- Documentation (100%) | Xin Huang | [14 empty] | 20: (40) 40 | (10) 10 | (10) 10 | (10) 10 | (40) 40 | (40) 40
PCB Design and Merging Subsystems (Due 4/14/2016)
- Merging subsystems (compression, spi, transmission) onto one Nordic Chip | Stephen Xia | [14 empty] | 21: (6) 6; 22: (14) 14; 23: (33) 33; 24: (23) 23; 25: (58) 58; 26: (40) 40 | (112) 112 | (39) 39 |  | (23) 23 | (174) 174
- Nordic PCB Design (100%) | Xin Huang | [14 empty] | 21: (6) 6; 22: (14) 14; 23: (19) 19 |  |  | (39) 39 |  | (39) 39
- Intan PCB Design (100%) | Tingkai Liu | [14 empty] | 21: (6) 6; 22: (14) 14; 23: (19) 19 |  | (39) 39 |  |  | (39) 39
- Server/Receiver (100%) | Yuan Gao | [14 empty] | 22: (9) 9; 25: (39) 39; 26: (60) 60 | (20) 20 |  |  | (88) 88 | (108) 108
- PCB Assembly and Testing (100%) | Tingkai Liu | [14 empty] | 24: (23) 23; 25: (59) 59; 26: (60) 60 |  | (54) 54 | (89) 89 |  | (142) 142
- New Ideal PCB Design (100%) | Xin Huang | [14 empty] | 28: (10) 10 |  |  | (5) 5 | (5) 5 | (10) 10
- Power Consumption vs. Sampling Rate Test (100%) | Tingkai Liu | [14 empty] | 28: (10) 10 | (5) 5 | (5) 5 |  |  | (10) 10
Cycle Four Documentation (Due 4/18/2016) (100%) | Stephen Xia | [14 empty] | 27: (24) 24 | (6) 6 | (6) 6 | (6) 6 | (6) 6 | (24) 24
Cycle Five Documentation (Due 5/2/2016) (100%) | Stephen Xia | [14 empty] | 28: (24) 24 | (6) 6 | (6) 6 | (6) 6 | (6) 6 | (24) 24
HOURS BY WEEK | [30 empty] | TOTAL
Stephen Xia |  | 3 | 5 | 11 | 5 | 14 | 7 | 12 | 5 | 15 | 11 | 10 | 9 | 80 |  | 1 | 7 | 10 | 15 | 13 | 30 | 61 | 8 | 15 | 20 | 15 | 40 | 40 | 7 | 12 | 481
Tingkai Liu |  | 3 | 5 | 11 | 7 | 13 | 7 | 13 | 5 | 15 | 11 | 10 | 9 | 72 |  | 1 | 7 | 10 | 15 | 10 | 30 | 61 | 8 | 15 | 20 | 15 | 40 | 40 | 7 | 12 | 472
Xin Huang |  | 3 | 5 | 11 | 2.5 | 6 | 4 | 10 | 5 | 5 | 3 | 3 | 4 | 10 |  | 1 | 5 | 3 | 8 | 6 | 18 | 36 | 8 | 15 | 20 | 10 | 40 | 40 | 7 | 12 | 300.5
Yuan Gao |  | 3 | 5 | 11 | 2 | 11 | 4 | 12 | 5 | 8 | 5 | 5 | 4 | 17 |  | 1 | 9 | 12 | 12 | 8 | 18 | 39 | 2 | 10 | 15 | 10 | 40 | 40 | 7 | 12 | 327
Total |  | 12 | 20 | 44 | 16.5 | 44 | 22 | 47 | 20 | 43 | 30 | 28 | 26 | 179 |  | 4 | 28 | 35 | 50 | 37 | 96 | 197 | 26 | 55 | 75 | 50 | 160 | 160 | 28 | 48 | 1580.5